{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":12,"n_cols":4,"rows_kept":12,"merged":[[0,0,0,3],[11,2,11,3]],"flags":["formulas_cached_only"]}
["附件1：2019届毕业设计（论文）相关工作布置及材料报送时间安排表"]
["序号","事项","时间节点","备注"]
[1,"成立领导小组、制定2019届毕业设计（论文）指导实施细则并报教务处备案","2018年12月7日前"]
[2,"选用、审核指导教师；提交校外毕业设计（论文）申请、协议","2018年12月14日前"]
[3,"完成选题、审题、分组工作；报送分组名单表","2018年12月28日前"]
[4,"下发任务书、完成开题","2019年1月4日前"]
[5,"落实毕业设计指导，检查指导老师到岗情况、学生出勤情况","2019年2月18日开始","院系两级检查"]
[6,"报送2019届毕业设计（论文）指导计划汇总表","2019年3月1日前"]
[7,"开展中期检查","2019年4月中旬","各系根据实际情况做时间微调"]
[8,"开展后期检查、完成毕业设计（论文）答辩前期组织","2019年5月中旬","各系根据实际情况做时间微调"]
[9,"毕业设计（论文）答辩","2019年5月27日-6月2日"]
[10,"其他","另文通知"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}